## User Guide
How to Use the Decision Log
Ref. #: This is a unique number for your reference. Just use a sequential code like Q101, Q102, etc., to make each entry easy to find.
Decision Date: Enter the date the decision was made.
Decision Summary: Write a short, clear title for the decision, like "Approve new marketing budget."
Rationale: Briefly explain why the decision was made. For example, "Align with Q3 growth targets."
Person Accountable (A): This is the single person who is ultimately responsible for the outcome of the decision.
Person Responsible (R): This is the person or team that will do the work to carry out the decision.
Deadline: Set a target date for when the work should be completed.
Status: Use a simple status like "Not Started," "In Progress," or "Complete" to track the decision's progress.
Notes/Roadblocks: Add any relevant details, updates, or issues that are preventing progress.
Next Steps: Clearly outline the immediate actions needed to move the decision forward.

## Q1 Board Decisions
Ref. # | Decision Date | Decision Summary | Rationale | Person Accountable (A) | Person Responsible (R) | Deadline | Status | Notes/Roadblocks | Next Steps
Q101 | 2025-05-02 | Approve new marketing budget | Align with Q3 growth targets | CEO (A) | Marketing Head (R) | 2025-05-15 | In Progress | Awaiting vendor quotes | Follow up on May 10
Q102 | 2025-05-02 | Hire additional IT support | Improve system uptime | COO (A) | HR Manager (R) | 2025-06-01 | Not Started | Job description pending | Draft Job description by May 12
... | ... | ... | ... | ... | ... | ... | ... | ... | ...